## Project Outline
Problem Statement
Want to design a cheap dash-cam with an easy user interface, small and cheap
Primary Motivation
I have not found a cheap and practical dashcam. They either take up too much space on front window, have very poor UI or expensive. The issue with expensive ones aside from cost is that they risk being stolen and too impractical to keep hiding/reinstalling each time you drive.
The goal is to make a dash cam with the following criteria:
Cheap
High quality recording (at least 720p)
Only records front
Long lasting battery: 10 hours
Bluetooth connectivity to a phone app
Small size
Secondary Motivation
Exposure to many aspects of product development; planning, electronic engineering, mechanical design, user experience.
Scope
Must have:
Record video instantly when turned on
At most £10 for the whole product except mechanical components
SD card to store videos, delete oldest video (not included in cost)
Rechargeable battery
Indicator LEDs for charging and pairing
ON/OFF switch
Button to pair
Takes up very little space on the driver window
Doesn’t feel cheap
Easy user interface
Phone app (both Android and iPhone) to view camera image
Easy mount to car window and rotate
Nice to have:
A cut-out to tell where camera is pointing
View recordings on phone app
Accelerometer to lock images
GPS
Time and date on videos
A way to view image from phone
Not in scope:
Large LCD to display camera view
Rear view recording

## Project Task Overview
Project Tasks Overview | [7 empty] | Risk |  |  | Status
[8 empty] | S | M | L
[6 empty] | Effort | S | 5 | 13 | 21 | Not started
[7 empty] | M | 13 | 21 | 34 | In progress
[7 empty] | L | 21 | 34 | 55 | Finished
Ongoing
Blocked
Tasks | Effort | Risk | Points | Date Started | Status | Notes | Notes 2 | Notes 3 |  |  | Cancelled
Project pre-plan | S | S | 5 | 2021-04-24 | Finished | Structure for plan- will use excel sheet, gantt charts
Project plan | S | S | 5 | 2021-04-24 | Finished | Please see the Gantt Chart sheet
Product block diagram | S | S | 5 | 2021-04-24 | Finished
Prototype | L | M | 34 |  | Ongoing
Video capture | S | S | 5 | 2021-04-24 | Finished
SD card research | S | M | 13 | 2021-04-24 | Finished
Video save files to SD card | S | M | 13 | 2021-04-24 | Finished | Need to save images within a video format. Likely to use avi. However, this needs to be written from scratch. There is an Arduino sketch that does this which can be copied. | Using jamezah's esp32 code to save jpegs to AVI files. Tested and confirm it works (records video and saves to sd card)
Video delete | S | S | 5 | 2021-04-24 | Finished | To delete a file is relatively easy. Just call a function
Bluetooth | L | L | 55 | 2021-05-01 | Cancelled | Did some initial research and it seems this will add too much complexity to the firmware. Will use alternative for first product which is a HTTP server that can be accessed via internet hotspot.
Bluetooth ESP32 research | S | S | 5 |  | Cancelled
Activate bluetooth on ESP32 | S | L | 21 | 2021-05-01 | Finished | Must use BT Classic. Arduino has very easy library for this.
Send image via bluetooth to PC or Smartphone? | M | M | 21 | 2021-05-02 | Cancelled | It's possible to make an app using Flutter. However decided to put this on hold because it has a steep learning curve relative to the rest of the project and high risk in terms of getting it to work as I've not had experience building phone apps.
Phone app using Flutter to view video | L | M | 34 | 2021-05-02 | Cancelled
OLED screen research | S | S | 5 | 2021-05-08 | Finished | Testing SSD1306, I2C, 128x32 OLED screen | Will use Arduino IDE for quick prototyping. Adafruit library will not work as can't swap I2C pins and the pins they use collide with camera, using u8g2 library instead. | u8g2 library works really well. Decided on 128x32 screen with scrolling text. Reason is it will have low power consumption and small size yet still displays info needed.
GPIO peripherals research | S | S | 5 | 2021-05-08 | Finished | See esp32 pinout spreadsheet. | See use_case_scenario text file | Will be using 4 buttons (up, down, okay, on)
Peripherals prototype | S | M | 13 | 2021-05-08 | Finished | Display message on screen, flash LED, connect to WiFi, save to SD card, stream to server | Used an already made Arduino code: https://github.com/jameszah/ESP32-CAM-Video-Recorder | 250mA being used during operation with all peripherals on. For 10 hours, need 2500mAh capacity. That is roughly 3 AAA NiMH batteries (at 800mAh each)
Schematic Design | M | S | 13 | 2021-05-08 | In progress
Battery Charger | L | S | 21 | 2021-05-08 | Ongoing
Battery Research | S | S | 5 | 2021-05-08 | Finished | If want 10 hours of use, need 3 AAA. Is this excessive? | Dash-cams typically don't have big batteries- customers are used to plugging them in all the time (saw multiple Amazon reviews which suggest this). A supercap to safely shut down should be enough. | Why supercap? No need for over/under charge protection circuit. Can charge/discharge virtually unlimited times. Works fine in warm temperatures like inside a car (unlike NiMH). Less dangerous than Li-Ion. Takes up less space.
Select Battery | S | S | 5 |  | Finished | Supercap. Still not decided on capacitance, however will go for 5.2V+ capacitors. | Will use 1 super-capacitor (no series or parallel connection as these appear to be more risky since over-charging may happen.
Find out time we need to safely shut down. | S | S | 5 |  | Finished | Arduino script has a function which safely saves the video and shuts down. This takes less than 1 second to perform. | I prefer to have the circuit shut down in around 2 seconds to display a 'goodbye message'.
Add power indicator LED | S | S | 5 |  | Finished
Finish schematic | M | S | 13 |  | Finished
PCB Spin 1 | M | M | 21 |  | Ongoing
Assign footprints | S | M | 13 |  | Finished
Purchase parts | M | S | 13 |  | Finished
Write firmware | S | S | 5 |  | Finished
Solder parts | S | S | 5 |  | Not started
Mechanical
Decide on shape of product | M | S | 13 |  | Finished | Initial thoughts were to have a single rectangular PCB (roughly 80mm x 40 mm with 10mm depth) but upon testing how it would look in the car, it was deemed too large
Solder parts | L | L | 55 |  | Finished | Soldering mostly complete however the board must be redesigned.
ESP32-CAM on pcb
Battery Charger
Buttons
LEDS
Mechanical

## Gantt Chart
Project Planner
| DASHCAM |  |  |  |  | Period Highlight: | 28 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
| ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE (x=cancelled) | PERIODS
 | time axis 2021-04-24 to 2021-10-09
[56 empty] | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | time axis 2021-04-24 to 2021-10-09
| Project Pre-Plan | 1 | 0.3 | 1 | 0.3 | 100%
| Create Gantt Chart | 1 | 0.3 | 1 | 0.3 | 100%
| Prototype | 1 | 10 | 1 | - | 40%
| ESP32-cam development env setup | 1 | 0.4 | 1 | 0.3 | 100%
| ESP32 SD card research | 2 | 0.1 | 1 | 0.1 | 100%
| ESP32 save video to SD card | 2 | 0.5 | 1 | 2 | 100%
| ESP32 delete video | 3 | 0.25 | 3 | 0.25 | 100%
| Bluetooth research on ESP32 | 3 | 0.75 | 3 | 0.5 | x
| Activate bluetooth on ESP32 | 4 | 3 | 3 | 0.25 | x
| Send video or image via bluetooth on ESP32 | 5 | 4 | 4 | - | x
| Phone app to display images by ESP32 | x | x | x | x | x
| HTTP/HTTPS server research | 4 | 0.5 | 3 | 0.5 | 100%
| OLED research | 5 | 1 | 5 | 1 | 100%
| Battery research | 6 | 0.5 | 6 | 0.5 | 100%
| Select battery | 6 | 0.5 | 6 | 0.5 | 100%
| Test super-capacitor with a basic circuit- calculations correct? | 7 | 0.25 | 7 | 0.25 | 100%
| Add battery to schematic | 7 | 0.5 | 7 | 0.25 | 100%
| Test battery charge prototype with full circuit | 7 | 0.25 | 8 | 0.25 | 100%
| Finish schematic | 8 | 2 | 8 | 1.5 | 100%
| Assign footprints | 10 | 0.5 | 9 | 1 | 100%
| PCB Spin 1 | 10 | 3 | 12 | 4 | 100%
| Purchase parts | 10 | 0.5 | 10 | 1 | 100%
| Order and wait for PCB | 14 | 4 | 14 | 12 | 100%
| Solder parts | 16 | 2 | 26 | 2 | 100%
| PCB Spin 2 | 20 | 3
Solder PCB 2
| Test PCB | 18 | 2 |  |  | 0%
| Write firmware | 20 | 5 | - | - | 0%
| Mechanical | 26 | 2 | - | - | 0%
| - | - | - | - | - | 0%
| - | - | - | - | - | 0%
| - | - | - | - | - | 0%
| - | - | - | - | - | 0%
| - | - | - | - | - | 0%
| - | - | - | - | - | 0%
| - | - | - | - | - | 0%

## Daily Notes
2021-05-15
Wired up test circuit with super capacitor. Charging with 24 ohm resistor, discharging to an LED
Calculating time to charge isn't very accurate as when you get closer to Vsupply the current reduces, so voltage increase slows down.
Found really useful calculator to calculate charge/discharge times: http://mustcalculate.com/electronics/capacitorchargeanddischarge.php?vfrom=3.8&vto=3.5&vs=0&c=1&r=10
Realised my circuit isn't ideal- slow charge, fast discharge
Worked on coming up with a design which will charge at maximum rate (500mA) and discharge at whatever the circuit needs (max 500mA). See LTSpice simulation circuit below.
Checked timing calculator, and the charging time is pretty slow, even with 500mA charge.Charging a bit more slower but having video recording on right away is better (even though turning it off less than 30 seconds will deplete battery).
Final thoughts:
LDO should work until ~3.46V
0 to 4.6V with supply voltage 4.8V, drawing 480mA (10R series resistor) = 32s
3.5V to 4.6V (with same current as above) = 19 seconds
4.6V to 3.46V (same current as above) = 2.8 seconds
2021-05-16
Tested Arduino script to see how quick it saves video. It's certainly less than 1 second (sent /stop command via http and I see the video gets saved less than a second).
The LCD should stay on for around 1-2 seconds to say a goodbye message, so this is plenty of tine.
ESP32 cam turns off at around 3.8V input (it's LDO has ~1V drop out as advertised)
With 5F capacitor, according to my calculations, it should take 6.7 seconds, and it takes around 7s in practice, so calculations seem accurate.
The same calculations show that 1F cap draining 200mA, to go from 4-3.5V will take over 2 seconds, which satisfies the specification.
1F cap also means the charge time will be a bit quicker.
Measuring capacitance required:
It = CV
It/V = C
dV = 4.6-3.5 = 1.1
I = 0.250 A (measured 300mA peak when everything was running, so in practice it is around 250mA avg)
dt = 2
(0.25*2)/1.1 = 0.45F
Will Use 0.47F
Charging time:
According to mustcalculate.com:
Will take 36 seconds to go to full charge from empty (will take 23 seconds if charging from 3.5V)
2021-05-22
Schematic checklist: | Done | Notes
I2C I/O expander | x
Power indicating LED | x | Green LED
Recording LED | x | Red LED
Button OK | x
Button Right | x
Button Left | x
Button ON/Off | x | Turns off device
Supercap | x
I2C OLED screen | x
USB power detect | x
ESP32 cam | x
ESP32 PSRAM | x
RTC? |  | Deep sleep current as stated in datasheet (>100uA) is too high, the esp32 will turn off in a few hours with our current super capacitor selection.
2021-05-23
https://www.buydisplay.com/download/ic/SSD1306.pdf
https://learn.adafruit.com/monochrome-oled-breakouts/downloads
https://www.buydisplay.com/download/interfacing/ER-OLED0.91-7_Interfacing.pdf
0.3mv Shottky Diodes are relatively expensive (£0.6 each). Will go for 0.39mV as they are £0.23 each and a 1F capacitor to reduce cost (0.47 and 1F capacitor are similar cost)
2021-05-29
Using 1F capacitor as the Schottky diode voltage drop was larger than assumed
Picking a lower ESR super capacitor (so it doesn't limit current below 500mA): https://www.digikey.co.uk/product-detail/en/illinois-capacitor/DGH105Q5R5/1572-1771-ND/7387509
2021-05-30
After analyzing the mechanical specification- I noticed the OLED has 0.62mm pitch (not 0.5 mm like previously assumed).
Will make my own footprint and a basic 3D image.
Will not use a connector as after analyzing the connector, it seems very possible to just solder it- saves buying another component and space.
2021-06-05
Continued working on what each PCB should contain.
Currently decided on this:
Front PCB |  | Back PCB
OLED |  | Camera
IO Expander |  | ESP32
SD card? |  | Power supply (including supercap)
USB Mini receptacle |  | If space, add SD card here so the only thing on the other PCB is the lower priority I2C peripherals only.
UI buttons (ok, left, right) |  | Power LED
Recording LED
2021-06-06
Working on PCB design and continuing working out which components go to which PCB.
Decided against having the SD card on a separate board due to worries that the SPI comms may corrupt.
New design:
Front PCB |  | Back PCB
OLED |  | Camera
IO Expander |  | ESP32
Power supply (including supercap) |  | SD card
USB Mini receptacle |  | If space, add SD card here so the only thing on the other PCB is the lower priority I2C peripherals only.
UI buttons (ok, left, right) |  | Power LED
Recording LED
Researched prices of 2 vs 4 layer pcbs. JLC PCB seems to be a lot cheaper than the alernatives (i.e. PCBWAY). There is only a small difference between 2 and 4 layer board. Will design 4 layer board.
Made progress on PCB design.
2021-06-12
Made further progress on PCB design. Components placed, need to route tracks.
2021-06-19
Finished routing tracks for front PCB
2021-06-20
Finished routing tracks for back PCB. Ran DRC check and passing. All tracks routes (except the 5 that are going to be connected via A FPC as expected).
Connected the two boards together with mouse bites.
JLCPCB charges ~£30 extra for vias smaller than 0.45 mm…
JLCPCB also charges an extra £30 for multi-panel designs.
I sent it off anyway as both 'panels' are the same width/height, hopefully they accept review.
If they accept review, I may buy their SMT service.
2021-06-27
JLCPCB accepted the review.
Choosing parts from JLCPCB, updating schem to include their part numbers. Will order the rest from Digikey
2021-07-18
JLCPCB charged extra because my PCB has "two designs".
The PCBs arrived this week. There is some soldering left to do. My aim is to solder the rest of the components, then test each section.
2021-07-25
First day of soldering: Using Hakko soldering iron with unleaded solder and flux, the soldering was relatively straight forward after I started using flux. Everything has been soldered on except the 24 way connectors.
The 24 way FFC connectors proved very difficult. I believe I must use a hot air gun, because the pins short very easily with a soldering iron and it's difficult to remove the shorts.
Some changes need to be made to the PCB:
1. Use a different FFC connector for the connection of the two boards. There is only a few wires needed anyway, using 24 way 0.5 mm pitch is too hard to solder without giving any benefits.
2. Leave more space between the mounting holes as components get in the way of the hex nuts
3. The SD card connector was back to front. The side where you solder IS the side where the SD card connects to…
4. Update footprint of the buttons, currently they have 3 GNDs but the actual buttons themselves only has 2 grounds in opposite corners.
5. Increase via size to minimum from JLCPcb so the PCBs are cheaper?
6. Add silkscreen for the esp32 uart connector.
Notes:
Buy more OLEDs, as they take a while to deliver
Check other components that we may need now that some of them were using during soldering
Buy twice as many as components needed, accidents happen more often than I thought they would
Going to see if the ESP32 works with the current connections.
Confirm the ESP32 can be programmed and can receive/transmit via UART