## Project Outline
Problem Statement
Want to design a cheap dash-cam with an easy user interface, small and cheap
Motivation
Cheap dashcams are really poor in terms of user interface, take up too much space on front window. Expensive ones risk being stolen and too impractical to keep hiding/reinstalling each time you drive.
The goal is to make a dash cam with the following criteria:
Cheap
High quality recording (at least 720p)
Only records front
Long lasting battery: 10 hours
Bluetooth connectivity to a phone app
Small size
Scope
Must have:
Record video instantly when turned on
At most £10 for the whole product except mechanical components
SD card to store videos, delete oldest video (not included in cost)
Rechargeable battery
Indicator LEDs for charging and pairing
ON/OFF switch
Button to pair
Takes up very little space on the driver window
Doesn’t feel cheap
Easy user interface
Phone app (both Android and iPhone) to view camera image
Easy mount to car window and rotate
Nice to have:
A cut-out to tell where camera is pointing
View recordings on phone app
Accelerometer to lock images
GPS
Time and date on videos
Not in scope:
LCD
Rear view recording

## Project Task Overview
Project Tasks Overview | [8 empty] | Risk |  |  | Status
[9 empty] | S | M | L
|  | Priority | A |  |  |  | Effort | S | 5 | 13 | 21 | Not started
|  |  | … |  |  |  |  | M | 13 | 21 | 34 | In progress
|  |  | D |  |  |  |  | L | 21 | 34 | 55 | Finished
Ongoing
Tasks | Effort | Risk | Points | Priority | Date Started | Status | Notes | Order of action
Project pre-plan | S | S | 5 | A | 2021-04-24 | Finished | Structure for plan- will use excel sheet, gantt charts
Project plan | S | S | 5 | A | 2021-04-24 | Finished | Please see the Gantt Chart sheet
Product block diagram | S | S | 5 | A | 2021-04-24 | Finished
Prototype | L | M | 34 | A |  | Ongoing
Video capture | S | M | 13 |  |  | In progress
Access SD card | S | M | 13 |  |  | Not started
Video save files to SD card | S | M | 13 |  |  | Not started
Video delete | S | S | 5 |  |  | Not started
Bluetooth | L | L | 55 |  |  | Not started
Bluetooth ESP32 research | S | S | 5 |  |  | Not started
Activate bluetooth on ESP32 | S | L | 21 |  |  | Not started
Send video via bluetooth to PC? | M | M | 21 |  |  | Not started
Phone app using Flutter to view video | L | M | 34 |  |  | Not started
Battery Charger | L | S | 21 |  |  | Not started
Battery Research | S | S | 5 |  |  | Not started
Select Battery | S | S | 5 |  |  | Not started
Select charge IC | S | S | 5 |  |  | Not started
Select safety IC | S | S | 5 |  |  | Not started
Develop battery charge prototype | M | L | 34 |  |  | Not started
Buttons | S | S | 5 |  |  | Not started
LEDs | S | S | 5 |  |  | Not started
PCB Spin 1 | M | M | 21 |  |  | Not started
ESP32-CAM | M | S | 13 |  |  | Not started
Battery Charger | M | M | 21 |  |  | Not started
Buttons | S | S | 5 |  |  | Not started
LEDS | S | S | 5 |  |  | Not started
Mechanical | L | L | 55 |  |  | Not started

## Gantt Chart
Project Planner | [9 empty] | 1
| DASHCAM |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
| ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
 | time axis 2021-04-24 to 2021-10-09
[56 empty] | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | time axis 2021-04-24 to 2021-10-09
| Project Pre-Plan | 1 | 0.3 | 1 | 0.3 | 100%
| Create Gantt Chart | 1 | 0.3 | 1 | 0.3 | 100%
| Prototype | 1 | 10 | 1 | - | 0%
| ESP32 video capture | 1 | 0.5 | 1 | - | 0%
| ESP32 access SD card | 2 | 0.5 | - | - | 0%
| ESP32 save video to SD card | 2 | 0.5 | - | - | 0%
| ESP32 delete video | 3 | 0.25 | - | - | 0%
| Bluetooth research on ESP32 | 3 | 0.75
| Activate bluetooth on ESP32 | 4 | 1 | - | - | 0%
| Send video or image via bluetooth on ESP32 | 5 | 1 | - | - | 0%
| Battery research | 6 | 0.5 | - | - | 0%
| Select battery | 6 | 0.5 | - | - | 0%
| Select charge IC | 7 | 0.25 | - | - | 0%
| Design battery protection | 7 | 0.5 | - | - | 0%
| Order parts for battery charger | 7 | 0.25
| Test battery charge prototype | 8 | 2 | - | - | 0%
| Test buttons | 10 | 0.5 | - | - | 0%
| Test LEDs | 10 | 0.5 | - | - | 0%
| PCB Spin 1 | 11 | 2 | - | - | 0%
| Develop phone app | 13 | 2 | - | - | 0%
| Mechanical | 15 | 4 | - | - | 0%
| - | - | - | - | - | 0%
| - | - | - | - | - | 0%
| - | - | - | - | - | 0%
| - | - | - | - | - | 0%
| - | - | - | - | - | 0%
| - | - | - | - | - | 0%
| - | - | - | - | - | 0%